## ASOC
These contracts are planned for advertisement by the Washington State Department of Transportation for Oct 1, 2024 through Sep 30, 2025. Only one state route is displayed per project. Some types of projects, e.g., chip seals, bridge painters, seismic retrofits, electrical updates, and guardrail updates, may involve regionwide work. For projects with fish barrier corrections, the fish passage Site Id(s) are listed in the comments. Please note the advertisement dates are tentative and some information may change after this report is issued. Projects are dependent on funding availability. For current information, please visit the Contract Ad and Award website at https://wsdot.wa.gov/business-wsdot/contracts/about-public-works-contracts/alerts-bulletins/contracts-planned-advertisement
*ESHB 2134, Section 502 requires that:
TRANSIT, BICYCLE, AND PEDESTRIAN ELEMENTS REPORTING By November 15th of each year, the department of transportation must report on amounts expended to benefit transit, bicycle, or pedestrian elements within all connecting Washington projects in programs I, P, and Z identified in LEAP Transportation Document 2024-2 ALL PROJECTS as developed March 6, 2024, in a manner consistent with past practices as specified in section 602, chapter 186, Laws of 2022.
Design Bid Build
Request for Qualifications (RFQ) / Ad Date | Type | Cost Range | Region | SR | Title and Work Description | County | WI Number | State | *502 | Comments
2024-10-07 | Bridge | Under 1M | Northwest | 542 | SR 542/Bagley Creek Bridge - Bridge Scour - Re-AD - Bridge scour 542/42 | Whatcom | A54240C
2024-10-07 | Bridge | 2 - 3M | Eastern | Multiple Routes | Eastern Region 2025 Bridge Repair - 2025 Bridge Repair | Adams | F22225A
2024-10-14 | Unique | 35 - 40M | Rail | Regionwide | CRISI Rural Rail Rehabilitation CW Branch - 2025 - Track rehabilitation along sections of the PCC System, will include repl |  | R00104D
2024-10-28 | Safety | 5 - 10M | South Central | 097 | US 97/Lateral A Intersection - Intersection Improvements - Construct roundabout | Yakima | E09704S
2024-10-28 | Unique | 5 - 10M | South Central | 082 | I-82/2 miles E of Donald Rd - Culvert Replacement - Replace culvert | Yakima | E08211Z | X
2024-11-04 | Bridge | Under 1M | AWV | 099 | SR 99/AWV Ballast Island Marker - Install monument along the waterfront to commemorate Ballast Island | King | U09920A
2024-11-04 | Unique | 1 - 2M | Capital Facilities | Regionwide | Geiger SMF Bldg 2 & Wandermere AMF PEO - PWP & OWS Install - NPDES - ER - Remove and replace existing pre-wash pads - D3PW003 & D311701 & D309701 | Spokane | S88866G | X
2024-11-07 | Unique | 5 - 10M | Ferries | Multiple Routes | Hybrid Electric Vessel Charging System - Procure terminal based VCSs and associated vessel receptacles | Kitsap, Snohomish, Kitsap, Snohomish | M90000R | X
2024-11-12 | Bridge | 3 - 4M | Northwest | 090 | I-90/EB East Channel Bridge - Modular Assembly Joints - Modular Assembly Joints - Br 90/40S | King | A09028A
2024-11-12 | Unique | 1 - 2M | North Central | 002 | US 2/West of Leavenworth - Slope Stabilization - Slope Stabilization | Chelan | B00209M
2024-11-12 | Resurface | 5 - 10M | North Central | 090 | I-90/E of Vantage to Moses Lake - Paving - Mill and fill | Grant | B09000P
2024-11-18 | Unique | Under 1M | Ferries | 020 FT FRIDAY | SR 20 Spur/Friday Harbor Trm - Visual Paging System Improvements - ADA hearing impaired visual paging system installation | San Juan | M04011A | X
2024-11-18 | Safety | 3 - 4M | North Central | 017 | SR 17/Cunningham Rd - Roundabout - Construct roundabout | Adams | B01701Y
2024-11-25 | Unique | 5 - 10M | Southwest | 014 | SR 14/Bingen Overpass - Construct grade separated rail crossing | Klickitat | D01419B | X | X
2024-11-25 | Resurface | 4 - 5M | Northwest | Regionwide | NWR North/Strategic Pavement Preservation 23-25 - Contract - HMA Crack Seal and Pavement Repairs | Skagit, Snohomish, Whatcom | A00023F
2024-12-02 | Major Construction | 20 - 25M | Olympic | 005 | I-5/Gravelly-Thorne Connector - Gravelly-Thorne Connector corridor improvements. | Pierce | C00507T | X | X
2024-12-02 | Unique | Under 1M | Ferries | 519 FT SEATTL | SR 519/Seattle Trm - Maritime Security Upgrades - Replace maritime security systems hardware and video cable replacement | King | M04841A
2024-12-09 | Unique | 5 - 10M | Northwest | Regionwide | NWR South/Strategic Pavement Preservation 23-25 - Contract - Asphalt Crack Sealing | Island, King, Skagit, Snohomish, Whatcom | A00023B
2024-12-16 | Safety | 1 - 2M | Northwest | 020 | SR 20/W Fakkema Road - Intersection Improvements - Compact Roundabout | Island | A02022D
2025-01-06 | Major Construction | 1 - 2M | Eastern | 090 | I-90/Harvard Rd Interchange - Ramp Meters - Install ramp meters and Variable Message Signs | Spokane | F09049Y
2025-01-06 | Major Construction | 70 - 80M | Northwest | 009 | SR 9/Marsh Road to 2nd Street Vic - Widening & Bridge Painting - Construct Second Bridge, Roadway Widening, and Painting Bridge 9/118 | Snohomish | A00912K | X | X
2025-01-09 | Bridge | 5 - 10M | Ferries | 304 FT | SR 304/Bremerton Trm Slips 1 & 2 - Dolphin Replacement - Replace vessel landing aids on bridges 304/18FT and 304/15FT | Kitsap | M03535A | X
2025-01-13 | Unique | 2 - 3M | Olympic | 109 | SR 109/N of Moclips Highway - Stabilize Slope - Repair unstable slope #1458 | Grays Harbor | C10901S
2025-01-13 | Safety | 3 - 4M | North Central | Regionwide | US 2 Et Al NCR Guardrail Update - 2025 - Guardrail | Chelan, Kittitas, King | B00008Y
2025-01-13 | Major Construction | 80 - 100M | Eastern | 395 | US 395/NSC Sprague Ave to Spokane River - Stage 3 - Construct new lanes | Spokane | F00015Q | X | X
2025-01-13 | Unique | 20 - 25M | Southwest | 105 | SR 105/Graveyard Spit - Dynamic Revetment and Dune Restoration - Construct an innovative nature-base dune and cobble berm | Pacific | D10524E
2025-01-13 | Unique | 5 - 10M | Northwest | 104 | SR 104/Lyon Creek - Fish Passage - Remove fish barrier (ID# 990253) | King | A10414A |  |  | Site Id(s): 990253.
2025-01-13 | Safety | Under 1M | Southwest | 142 | SR 142/0.7 Miles E of Appleton Rd to School Dr - Trail Improvements - Upgrade ADA facilities within the limits of the paver 414214P | Klickitat | D14214C | X
2025-01-13 | Unique | 5 - 10M | Northwest | 002 | US 2/Sexton Creek to Pilchuck River - Fish Passage - Remove Fish Barrier (ID # 995103) | Snohomish | A00207A |  |  | Site Id(s): 995103
2025-01-21 | Major Construction | 25 - 30M | Northwest | 526 | SR 526/Corridor Improvements - Corridor Mobility Improvements | Snohomish | A52604K | X | X
2025-01-21 | Safety | 5 - 10M | Northwest | 002 | US 2/Corridor Safety Improvements - Corridor Safety Improvements | Snohomish | A00217A |  | X
2025-01-21 | Safety | 2 - 3M | North Central | 026 | SR 26/1st Ave - Roundabout - Construct Roundabout | Adams | B02601V
2025-02-03 | Unique | 3 - 4M | Olympic | Regionwide | 2023 Regionwide Adaptive Management - Fish Passage - Barrier Repairs (18.0021 5.40,22.0507 0.10,990178,990400,996735) | Clallam, Grays Harbor, Jefferson, Mason | C00023F | X |  | Site Id(s): 18.0021 5.40, 22.0507 0.10, 990178, 990400, 996735
2025-02-03 | Safety | 2 - 3M | Olympic | Multiple Routes | SR 702, SR 510, & SR 507 CRAB Bundle #1A - Construct compact roundabouts | Thurston | C50742R
2025-02-03 | Unique | Under 1M | Northwest | 005 | I-5/NB Spokane St - Install Ramp Meter - Ramp Meter Installation | King | A00526Q | X
2025-02-10 | Resurface | 3 - 4M | Northwest | 018 | SR 18/EB C St SW Vic to Green River - Paving & Joint Replacement - HMA Paving and Joint Replacement Bridge 18/9 | King | A01803A
2025-02-10 | Resurface | 5 - 10M | Northwest | 005 | I-5/SB Nooksack River to Blaine - Paving - HMA Paving | Whatcom | A00595J
2025-02-10 | Resurface | 3 - 4M | Northwest | 090 | I-90/EB Mercer Slough to 150th Ave SE - Paving - HMA Paving | King | A09052N
2025-02-10 | Resurface | 5 - 10M | Northwest | 525 | SR 525/I-405 I/C to SR 99 Vicinity - Paving & ADA Compliance - HMA Paving and ADA Compliance | Snohomish | A52500D
2025-02-18 | Unique | 1 - 2M | Southwest | 508 | SR 508/0.3 Miles E of Bergen Road - Engineered Log Jam - Embankment protection to prevent erosion of the highway | Lewis | D50825J
2025-02-24 | Resurface | 5 - 10M | Olympic | 112 | SR 112/E of Sail River to E of E Twin River - Paving and Preservation - Overlay paving, drainage, guardrail and signing | Clallam | C11200P | X
2025-02-24 | Major Construction | 3 - 4M | South Central | 410 | SR 410/Rock Creek Vic - Chronic Environmental Deficiency - Replace culvert, raise roadway, and realign creek | Yakima | E41001O
2025-03-03 | Major Construction | 10 - 15M | Northwest | 531 | SR 531/43rd Ave NE to 51st Ave NE - Improvements - Improvements (Connecting Washington Account) | Snohomish | A53160K |  | X
2025-03-03 | Unique | Under 1M | Northwest | Regionwide | I-90, SR 202, SR 203, & SR 900 - Adaptive Management - Adaptive Management of 4 sites | King | A00022H | X
2025-03-05 | Resurface | 1 - 2M | Ferries | 305 FT WINSLO | SR 305/Bainbridge Island Trm - NE Parking Lot Pavement Rehabilitation - Resurfacing/rehabilitation of upland parking area | Kitsap | M03480A | X
2025-03-10 | Resurface | 1 - 2M | Northwest | 099 | SR 99/Tunnel - Pavement Texturing - Pavement Texturing | King | A09940A
2025-03-10 | Unique | Under 1M | Capital Facilities | 005 | I-5/Gee Creek NB SRA - Rehabilitate RV Dump Station- Re-Ad - Rehabilitate existing RV dump station | Clark | H00506F
2025-03-17 | Unique | 2 - 3M | Olympic | 112 | SR 112/Clallam Bay 2023 - Emergency Project - Repair unstable slope #2947 | Clallam | C11215E
2025-03-17 | Bridge | Under 1M | Eastern | 194 | SR 194/Busch Bridge at Port of Almota - Bridge Rehab - Rehab Bridge 194/1 with new concrete deck surface and modify girders. | Whitman | F19400L
2025-03-24 | Resurface | 4 - 5M | Eastern | 021 | SR 21/SR 260 to US 395 - Chip Seal - Chip Seal with Basic Safety Restoration | Adams, Franklin | F02100U
2025-03-24 | Resurface | 4 - 5M | Eastern | 395 | US 395/Hafer Rd to Chewelah - Paving - Hot Mix Asphalt paving with basic safety restoration & Complete Streets | Stevens | F39520C
2025-03-31 | Resurface | 4 - 5M | Eastern | 395 | US 395/Lind Coulee Bridge to I-90 - SB Lanes Only - Paving - HMA paving with basic safety restoration | Adams | F39508B
2025-03-31 | Unique | 20 - 25M | South Central | 224 | SR 224/Red Mountain Vicinity Improvements - Improve intersections, add lanes and bike & pedestrian facilities | Benton | E22407R | X | X
2025-03-31 | Safety | 3 - 4M | Northwest | 020 | SR 20/Campbell Lake Road - Intersection Improvements (Local-WSDOT Lead) - Construct Three-Legged Roundabout (GCB 3267) | Skagit | A02028E
2025-04-07 | Unique | Under 1M | Southwest | 432 | SR 432/Washington Way Signal Replacement - Upgrade Signal System | Cowlitz | D43216S
2025-04-07 | Safety | Under 1M | North Central | 282 | SR 282/Nat Washington Way - Roundabout - Construct roundabout | Grant | B28201E | X
2025-04-14 | Major Construction | 2 - 3M | Northwest | 090 | SE 104th St Stream Restoration - Fish Passage (Barrier #935013) | King | A09070L |  | X
2025-04-14 | Major Construction | 100 - 200M | Eastern | 395 | US 395/NSC Sprague Ave to Spokane River - Stage 2 - Construct new lanes | Spokane | F00015P | X | X
2025-04-21 | Unique | Under 1M | South Central | 395 LX | US 395/Kartchner St I/C - NB Ramp Terminal Improvements - Construct compact roundabout | Franklin | E39508Q | X
2025-04-21 | Major Construction | 50 - 60M | Olympic | 510 | SR 510/Yelm Loop - New Alignment Phase 2 - New alignment | Thurston | C51029A | X | X
2025-04-22 | Bridge | 2 - 3M | Ferries | 525 FT MUKILT | SR 525/Mukilteo Trm - Left Wingwall Rehabilitation and Repair - Left Wingwall Rehabilitation and Repair | Snohomish | M04422A | X
2025-04-23 | Unique | 15 - 20M | Ferries | 160 FT | SR 160/Southworth Trm - Terminal Building Replacement - Replace existing ferry terminal building on trestle and relocate upland | Kitsap | M05003C
2025-05-05 | Bridge | 5 - 10M | Northwest | 090 | I-90/EB Mercer Slough Bridge - Rehabilitation - Bridge Rehabilitation Br 90/43S | King | A09029A
2025-05-12 | Safety | 2 - 3M | Eastern | 090 | I-90/Guardrail Basic Safety - Rehabilitation - Remove, replace and rehabilitate existing guardrail | Spokane, Lincoln, Adams | F09019G
2025-05-19 | Resurface | 5 - 10M | Northwest | 020 | SR 20/Burlington to Sedro-Woolley - Corridor Improvements - Corridor Improvements | Skagit | A02061A
2025-05-27 | Major Construction | Under 1M | Southwest | 508 | SR 508/0.1 Miles East of Guerrier Rd - Embankment Erosion Repair Phase 2 - Embankment protection | Lewis | D50825E | X
2025-06-02 | Bridge | Under 1M | Northwest | 099 | SR 99/NB 1st Ave S Bridge-Tower Mitigation & Watertight Door Replacement - Replace Watertight Door - Bridge 99/530E | King | A09926V
2025-06-16 | Bridge | Under 1M | Southwest | 014 | SR 14/E of Slide Bridge - Repair Crib Wall - Repair or replace deteriorating timber crib wall just east of Br. 14/104 | Skamania | D01414G
2025-06-23 | Unique | Under 1M | Olympic | 106 | SR 106/McReavy Rd Vicinity - Culvert Repair - Repair existing culvert WSDOT0000786471 | Mason | C10612B | X
2025-06-30 | Unique | 5 - 10M | Ferries | 519 FT SEATTL | SR 519/Seattle Trm - Pile Corrosion mitigation - Pile Corrosion mitigation | King | M04879A | X
2025-07-01 | Unique | Under 1M | Ferries | 020 FT ORCAS | SR 20 Spur/Orcas Island Trm - Visual Paging System Improvements - ADA hearing impaired visual paging system installation | San Juan | M04510A | X
2025-07-01 | Unique | 5 - 10M | Ferries | Regionwide | WSF Terminal Wait Times Traveler Information System - Research automatic queue detection and wait time information | Island, Jefferson, King, Kitsap, Pierce | M98609A
2025-07-07 | Bridge | 5 - 10M | Northwest | 529 | SR 529/SB Steamboat Slough Bridge - Bridge Painting - Bridge Painting Bridge 529/20W | Snohomish | A52906K
2025-07-08 | Unique | Under 1M | Ferries | 304 FT BREMER | SR 304/Bremerton Trm - Illumination System Rebuild - Replace existing light fixtures and deficient luminaire poles as needed | Kitsap | M03544A | X
2025-07-14 | Bridge | 3 - 4M | Ferries | 160 FT VASHON | SR 160/Vashon Trm Slip 2 - Vehicle Transfer Span Rehabilitation - Rehabilitation/retrofit of steel girder movable bridge 160/103FT | King | M05242A | X
2025-07-21 | Safety | 4 - 5M | Southwest | 500 | SR 500/NE Robinson Rd and NE 3rd St - Intersection Safety Improvements - Improve safety at two intersections | Clark | D50018S
2025-07-21 | Major Construction | 4 - 5M | Olympic | 162 | SR 162/SR 410 Interchange - Construct Roundabouts - Design for the SR 162/SR410 roundabouts | Pierce | C16202C | X
2025-07-28 | Unique | 5 - 10M | South Central | Regionwide | SCR 25-27 Region Wide - Strategic Pavement Preservation - Select low cost repairs to extend the roadway life |  | E00007M | X
2025-08-04 | Safety | Under 1M | Southwest | 4 | SR 4/Crawford Bridge Pedestrian Illumination | Cowlitz | N/A
2025-08-04 | Bridge | 4 - 5M | Southwest | 504 | SR 504/Spirit Lake Outlet Br - Emergency Replacement - Replacing Bridge #504/107 - Spirit Lake Outlet Br | Skamania | D50424F
2025-08-04 | Safety | 3 - 4M | Olympic | 162 | SR 162/Orville Rd E Intersection - Roundabout - Construct a roundabout | Pierce | C16211R
2025-08-11 | Bridge | 15 - 20M | Ferries | 304 FT BREMER | SR 304/Bremerton Trm Slips 1 & 2 - Vehicle Transfer Span Replacement - Replace existing movable bridges 304/18FT and 304/15FT | Kitsap | M03534A | X
2025-08-14 | Unique | 5 - 10M | Ferries | 305 FT EAGHBR | SR 305/Eagle Hbr Maint Facility - Welding Shop Building Replacement - Replacement of existing welding shop building on Slip E trestle | Kitsap | M03731A | X
2025-08-18 | Safety | 1 - 2M | South Central | 012 | US 12/Eschbach Rd - Intersection Safety Improvements - Construct intersection improvements | Yakima | E01216X
2025-08-18 | Safety | Under 1M | South Central | 012 | US 12/Ackley Rd/Clover Lane - Intersection Safety Improvements - Construct intersection improvements | Yakima | E01216Z
2025-08-25 | Major Construction | 10 - 15M | Northwest | 531 | SR 531/51st Ave NE to 59th Ave NE - Improvements - Improvements (Connecting Washington Account) | Snohomish | A53160L | X
2025-09-02 | Unique | 1 - 2M | Capital Facilities | Regionwide | Bingen SMF - Wash Pad Water Remediation - NPDES - SWR - Install new wash pad and heated wash bay - BIN D311701 | Klickitat | S88843T | X
2025-09-08 | Bridge | 1 - 2M | Northwest | 020 | SR 20/Deception and Canoe Pass Bridges - Soil Abatement - Soil Abatement | Skagit, Island | A02026T
2025-09-08 | Bridge | 5 - 10M | Northwest | 099 | SR 99/Spokane Street Bridge - Expansion Joint Modification - Expansion Joint Modification Bridge 99/538 | King | A00502C
2025-09-15 | Unique | 2 - 3M | North Central | Regionwide | NCR Strategic Pavement Preservation 25-27 - Repair and preserve pavements throughout NCR | Adams | B00008V | X
2025-09-15 | Major Construction | 5 - 10M | Northwest | 018 | SR 18/Preston Mill Park Mitigation - Wetland and Stream Mitigation | King | A01820L
2025-09-22 | Safety | 2 - 3M | Olympic | 702 | SR 702/8th & 40th St - CRAB Bundle #1B - Construct a compact roundabout | Pierce | C70205A
2025-09-26 | Unique | 1 - 2M | Ferries | 163 FT PTDEFI | SR 163/Point Defiance Trm - Toll Booth 1 - Toll Booth 1 | Pierce | M04618A | X
2025-09-29 | Safety | 3 - 4M | Olympic | 160 | SR 160/Long Lake Rd SE - Roundabout - Construct a roundabout | Kitsap | C16011B
2025-09-29 | Safety | 2 - 3M | Olympic | 302 | SR 302/118th Ave NW Intersection - Roundabout - Construct a roundabout | Pierce | C30212R