## 2024 Jan Update
Important Notice This report includes anticipated dates, methods of delivery and estimated contract values that are based on the best available information at the time the report was last updated. The Washington State Department of Transportation (WSDOT) will update this report semi-annually and endeavors to ensure that the information contained herein is as accurate as possible, but cannot make any guarantees as to ultimate outcomes. Regardless of confidence rating, WSDOT is not responsible or liable to any parties if elements of this report are used to influence or inform the business decisions of those parties. * Information about delivery method may be useful to firms interested in (a) preparing for alternative project delivery scenarios or (b) identifying projects where work on preliminary design may result in the inability to work on subsequent design elements. ** These confidence ratings are qualitative judgements about whether the information presented will match the ultimate project scenario. See above notice.
Project | Description | Advertisement | Delivery Method* | A & E Category | Contract Execution Date | Estimated End Date | Region | Potential Value | Confidence Rating** | Project Contact Information
SR 167/SR 161 to SR 410 – Rebuild Interchange Project. AKA 2a | Provide engineering and related technical services as part of the Design Build Team to deliver the project. | 2024-01-17 | Design-Build | Geotechnical Engineering Transportation Design Engineering Transportation Construction Support | Fall 2024 | Spring 2028 | OR | $165 - 215M | High | Steve Fuchs, (360)701-9413, FUCHSS@wsdot.wa.gov
I-5/E Fork Lewis River Bridge NB - Replace Bridge | Provide engineering and related technical services as part of the Design Build Team to deliver the project. | 2024-02-26 | Design Build | Transportation Design Engineering | 2025-03-01 | 2029-03-31 | SW | $80-90 million | HIgh | Susan Fell, swrcceo@wsdot.wa.gov
I5/Guide Meridian Interchange Vicinity-Fish Passage | Provide engineering and related technical services as part of the Design Build Team to deliver the project. | 2024-04-08 | DB | Transportation Design Engineering | 2025-05-05 | Feb. 2027 | NWR | $50 million | Medium | Shane Spahr, (360) 757-5990, SpahrS@WSDOT.WA.GOV
I-5/Secret Creek - Fish Passage | Provide engineering and related technical services as part of the Design Build Team to deliver the project. | 2023-08-28 | DB | Transportation Design Engineering | 2024-05-15 | Dec. 2026 | NWR | $50 million | High | Shane Spahr, (360) 757-5990, SpahrS@WSDOT.WA.GOV
Geotechnical Engineering & Project Delivery 2023 - 2027 (FE-2) | The State Geotechnical Office requires the services of a Geotechnical Engineering firm to provide specialized geotechnical engineering expertise, report development, project delivery, construction support and related activities on large complex transportation projects statewide. | Feb - Mar 2024 | All Delivery Methods DBB, DB, PDB, EMERG. | Geotechnical Engineering Transportation Design Engineering Transportation Construction Support | TBD | 2027-12-31 | HQ | $10 Million | High | Andrew Fiske, (360)709-5456, fiskea@wsdot.wa.gov
Geotechnical Engineering & Project Delivery 2023 - 2027 (FE-3) | The State Geotechnical Office requires the services of a Geotechnical Engineering firm to provide specialized geotechnical engineering expertise, report development, project delivery, construction support and related activities on large complex transportation projects statewide. | Feb - Mar 2024 | All Delivery Methods DBB, DB, PDB, EMERG. | Geotechnical Engineering Transportation Design Engineering Transportation Construction Support | TBD | 2027-12-31 | HQ | $4 Million | High | Andrew Fiske, (360)709-5456, fiskea@wsdot.wa.gov
SR 518, Tukwila International Boulevard Station Bus Rapid Transit | This Sound Transit funded project consists of a new Bus Rapid Transit station. The station would serve eastbound and westbound BRT vehicles located at-grade within the STATE SR 518 right-of-way. The station will be east of the Tukwila International Boulevard (SR 99) interchange adjacent to the existing Tukwila International Boulevard Link light rail station. | 1/18/24 - 12/20/24 | Design Build | Project | 2025-01-30 | 2027-06-20 | NW | $100-200 Million | Medium | Andrew Ziegler, (425)450-2570, zieglea@wsdot.wa.gov
Capital Facilities General Engineering Contract | General engineering support for Capital Facilities projects of various delivery methods. Project phases may include but are not limited to: • Scoping / Study / Investigation • Schematic Design • Design Development • Construction Document • Bidding • Construction • Project Closeout | July - Aug 2024 | All Delivery Methods DBB, DB, PDB, EMERG. | Transportation Design Engineering | 2025-01-30 | 2029-01-30 | HQ | $4 Million | High | Chris Linden, 360-705-6829, chris.linden@wsdot.wa.gov
Bingen SMF – Wash Pad Water Remediation - SWR | Provide civil and architectural design and related technical services as part of the Facilities Team to deliver plans and specifications for the trush wash building at the exsiting maintenance facility. | Fall 2024 | DBB | Facilities Architectrual Services | 2024-09-01 | 2025-11-30 | SWR | $600,000 - $700,000 | Hgh | Young Kim, 360-705-7365, young.kim@wsdot.wa.gov
Geiger SMF Bldg 2 and Wandermere AMF/PEO - PWP & OWS Install - NPDES -ER | Provide construction management, engineering and related technical services as part of the Facilities Team to deliver the construction phase of the project. | Winter 2024 | Design-Bid-Build | Construction Management and Inspection Services | TBD | 2025-06-30 | ER | $150,000 | High | Sam Leiren, 360-705-7353, samuel.leiren@wsdot.wa.gov
I-5/Gee Creek NB RV Dump Station Rehabilitation SWR | Provide civil and architectrual design and relted technical services as part of the Facilities Team to deliver plans and specifications for the RV dumping stations at the existing stations at the existing safety rest area. | Winter 2024 | DBB | Facilities Architectrual Services | 2025-02-01 | 2025-12-01 | SWR | $500,000 - $600,000 | High | Young Kim, 360-705-7365, young.kim@wsdot.wa.gov
I-90/Winchester WB SRA - Water Rehabilitation - NCR | Provide engineering and related technical services as part of the Facilities Team to deliver the construction phase of the project | Winter 2024 | Design-Bid-Build | Facilities Civil Engineering | TBD | 2025-06-30 | NCR | 40000 | High | Sam Leiren, 360-705-7353, samuel.leiren@wsdot.wa.gov
SR 167/I-5 to SR 161 - New Expressway. AKA 2b | Provide engineering and related technical services as part of the Design Build Team to deliver the project. | 2024-09-09 | Progressive Design-Build | Geotechnical Engineering Transportation Design Engineering Transportation Construction Support | Summer 2025 | Late 2029 | OR | $375M - $475M | Medium | Steve Fuchs, (360)701-9413, steve.fuchs@wsdot.wa.gov
Wenatchee RHQ Bldg. 2 Roof Replacment and Vehicle Exhaust System - NCR | Provide architectural design and related technical services as part of the Facilities Team to deliver plans and specifications for roof replacment, installation of vehicle exhaust system, and HVAC upgrades | Spring 2025 | DBB | Facilities Architectrual Services | 2025-05-01 | 2025-08-30 | NCR | $600,000 - $700,000 | Medium | Keith Rosevear, 360-705-7307, keith.rosevear@wsdot.wa.gov
SR 410 Greenwater SRA – Design and Site Improvements - NWR | Provide architectural design and related technical services as part of the Facilitis Team to deliver plans and specifications for a future safety rest area and temporary facilities. | Spring 2025 | DBB? | Facilities Architectrual Services | 2025-04-01 | 2025-06-30 | NWR | $500,000 | Medium | Keith Rosevear, 360-705-7307, keith.rosevear@wsdot.wa.gov
WSDOT
Projected Design Opportunities for Consultants